# Digital Equity Forum Timeline and Milestones

|  |  |
| --- | --- |
| **Milestone** | **Date** |
| **Digital Equity Forum At-Large Meeting #1*** Project kickoff
 | December 9 |
| **Small Group Workshop Option A** | February 24 2:00 – 4:00 pm |
| **Small Group Workshop Option B** | March 24 2:00 – 4:00 pm |
| **Community Listening Session #1** | March 29 5:00 – 6:30 pm |
| **Community Listening Session #2** | March 30 12:00 noon – 1:30 pm |
| **Digital Equity Forum At-Large Meeting #2*** 2022 Work Plan - Values-based decision framework
* 2022 Work Plan - Mission, vision, and values
* 2022 Work Plan - Key definitions
 | April 7, 1:00 – 4:00 pm |
| **Community Listening Session #3**  | May 10 5:00 – 6:30 pm |
| **Community Listening Session #4** | May 11 12:00 noon – 1:30 pm |
| **Digital Equity Forum At-Large Meeting #3*** Interim report
* Community listening session findings
 | June 9, 1:00 – 4:00 pm |
| **Small Group Recommendations Development Workshop #1*** Recommendation development
 | July 14 Time TBD |
| **Small Group Recommendations Development Workshop #2*** Recommendation refinement
 | August Date/Time TBD |
| **Digital Equity Forum At-Large Meeting #4*** Draft recommendations
 | September 15, 1:00 – 4:00 pm |
| **Digital Equity Forum At-Large Meeting #5*** Finalize recommendations, consensus and approval
* Acknowledgements and gratitude
 | October 20, 1:00 – 4:00 pm |
| **WSBO and Office of Equity write final report and transmit to the Legislature.** | October 20 – January 1, 2023 |